## Use case
NO. | Feature | Use cases | Guest | Student | Teacher | Reviewer | Designer | CRDD Staff | CRDD Head | System Admin | Use case description
1 | Home page | Home page | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | homepage (logout, back to home, back to index)
2 | Register | Register | ✓ | [7 empty] | This is the screen that allows users to register in the system by entering the following information: Full name, email/mobile, password; The user then needs to verify by entering the "authentication code" emailed to him/her before being able to access the system.
3 | User Login | Login | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | This is a screen which allows the user to enter email or phone & password to login; on this page, there are also options for user to register new information or reset the password for the case you forget it
4 | User Authorization | Authorization and Access Control | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly)
5 | Change Password | Users want to change their current password for better security |  | ✓ | ✓ |  | ✓ | ✓ | ✓ | ✓ | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice)
6 | Reset Password | Users forget their password and want to reset a new password. |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | "The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. "
7 | User Profile | View profile |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |  | View Profile is a function that allows users to view their personal information on a website or application. When selecting this function, the user will be directed to a page displaying their personal information.
8 | Account list | View account list Search account | [7 empty] | ✓ | - Show and search all user accounts(user id, full name, email, mobile, user name, password, status) - The user is redirected to the account details on his/her clicking on the account.
9 | Add new Account | Add new account | [7 empty] | ✓ | Add new account by admin
10 | Account details | Edit information of user by admin | [7 empty] | ✓ | This is a screen that allows the admin to change the user's information
11 | Setting List | View or edit setting | [7 empty] | ✓ | Show a list of settings (id, name, type, value, display order, action) +Allow admins to search settings by name + From each setting, admin can choose to enable/disable or edit
12 | Setting Details | Create new setting | [7 empty] | ✓ | Show detailed user information (name*, type, value, display order,description), from that allow the user to add new setting information
13 | Curriculum List | View list curriculum | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | View Curriculum - Search by code - Search by name
14 | New Curriculum | Add new Curriculum | [5 empty] | ✓ | ✓ | ✓ | New Curriculum - Create curriculum
15 | Curiculum Overview | View overview Curriculum | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Curriculum Overview - view overview of curriculum
16 | Curiculum Edit | Edit Curriculum | [5 empty] | ✓ | ✓ | ✓ | Curriculum Edit - Edit infomation of curriculum
17 | PLO_List | List all PLO | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Show list all PLO
18 | PLO_Details | Update/Remove PLO | [7 empty] | ✓ | Allow update , create plo
19 | PLO_Import | Import new PLO | [7 empty] | ✓ | Import list plo from excel
20 | PLO_PO_Mapping | System Admin | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Relationship PLO_PO
21 | PLO_Subject_Mapping | System Admin | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Relationship PLO_Subject
22 | PO_List | View List PO | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | View List PO
23 | PO_Details | Edit list PO | [5 empty] | ✓ | ✓ | ✓ | Edit list PO
24 | Subject list | View Subject list | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | View Subject list
25 | New Subject | Add new subject |  |  |  |  | ✓ | ✓ | ✓ | ✓ | Add new subject
26 | Subject import | import new subject |  |  |  |  | ✓ | ✓ | ✓ | ✓ | import new subject
27 | Subject Details | Edit subject |  |  |  |  | ✓ | ✓ | ✓ | ✓ | Edit subject
28 | New Crriculum Subject | Add new Crriculum Subject |  |  |  |  | ✓ | ✓ | ✓ | ✓ | Add new Crriculum Subject
29 | Crriculum Subject Details | Edit Crriculum Subject |  |  |  |  | ✓ | ✓ | ✓ | ✓ | Edit Crriculum Subject
30 | Combo List | View combo list | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | View Combo List
31 | Combo Details | View combo Details | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | VIew Combo Details
32 | Elective list | View elective list |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | View elective list
33 | Elective detail | Edit or add new elective |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Edit or add new elective
34 | Decision list | View Decision | [6 empty] | ✓ | ✓ | Decision List - Search by decision_no - Search by approved date null
35 | Decision overview | View overview Decision |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Decision overview - view decision
36 | New Decision | Add new Decision | [6 empty] | ✓ | ✓ | New Decision - AddnewDecision
37 | Decision detail | Edit Decision | [6 empty] | ✓ | ✓ | Decision detail - Edit decision - Update decision for curriculum
38 | Syllabus List | View Syllabus List |  | ✓ | ✓ |  |  | ✓ | ✓ | ✓ | View Syllabus List
39 | Syllabus Overview | View Syllabus Overview |  | ✓ | ✓ |  |  | ✓ | ✓ | ✓ | View Syllabus Overview
40 | New Syllabus | Add New Syllabus | [5 empty] | ✓ | ✓ | ✓ | Add New Syllabus
41 | Syllabus Import | Syllabus Import | [5 empty] | ✓ | ✓ | ✓ | Syllabus Import
42 | Content List | View Content List | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | View list content
43 | Content Detail | View Content Detail | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | View detail content
44 | Subject Predecessors | View Subject Predecessors | ✓ | ✓ | ✓ | ✓ | ✓ |  | ✓ | ✓ | View subject predecessors
45 | Subject Successors | View Subject Successors | ✓ | ✓ | ✓ | ✓ | ✓ |  | ✓ | ✓ | View subject successors
46 | List Quesiton | View List Question |  | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | List question
47 | Question detail | Edit question | [5 empty] | ✓ | ✓ | ✓ | Edit question
48 | Curiculum Subject List | View Curiculum Subject List | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | View Curiculum Subject List
49 | Submit_List | View Submit List |  |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | View All Submit list
50 | Submit_Details, Discustion | Edit,Add,Discussion |  |  |  | ✓ | ✓ | ✓ | ✓ | ✓ | Edit,Add,Discussion
51 | Import CLO | Import list CLO | [5 empty] | ✓ | ✓ | ✓ | Allowed Import list CLO
52 | CLOs_PLOs | Mapping CLOs_PLOs | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Relationship between CLOs and PLOs
53 | CLO Details | Edit,Add CLOs | [5 empty] | ✓ | ✓ | ✓ | Allow administratorEdit,Add CLOs
54 | CLO List | View List CLO | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | Show list CLO

## Product
THE APPLICATION DEVELOPMENT PROJECT TOPIC, PRODUCT BACKLLOG
NO. | Screen/Function Name | Feature | User Access WorkFlow | Curriculum WorkFlow | Syllabus WorkFlow | Subject WF | Decision WorkFlow | User Management WF | Setting WorkFlow | Subject Successors WF | Syllabus Submit WF | Subject Predecessors WF | Screen/Function Details | Student No | In-charge Full Name | Status | SRS | SDS | Planned | Actual | Update | Update Details
1 | Home page | Common | x | x | x | x | x | x | x | x | x | x | Home page -view profile - logout | HE160555 | Trần Đình Hiệp | Done | Done | Done | Iter1 | Iter1 | Iter4 | Edit UI
2 | Register | Common | x | [9 empty] | Register | HE163982 | Quản Ngọc Trung | Done | Done | Doing | Iter1 | Iter1 | Iter4 | Add password encryption.
3 | User Login | Common | x | x | x | x | x | x | x | x | x | x | Login | HE163528 | Nguyễn Tiến Thành | Done | Done | Doing | Iter1 | Iter1 | Iter4 | Login password is case sensitive
4 | User Authorization | Common | x | x | x | x | x | x | x | x | x | x | Authorization and Access Control | HE163528 | Nguyễn Tiến Thành | Done | Done | Doing | Iter1 | Iter1 | Iter4 | Authorization to use the filter, error screen not allowed to access
5 | Change Password | Profile Management | x | [9 empty] | Users want to change their current password for better security | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter1 | Iter1
6 | Forget Password | Common | x | [9 empty] | Users forget their password and want to reset a new password. | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter1 | Iter1 | Iter4 | - Add toast successfull after reset password
7 | User profile | Profile Management | x | [9 empty] | View profile - update profile | HE160555 | Trần Đình Hiệp | Done | Done | Done | Iter1 | Iter1 | Iter4 | - Update validate input
8 | Account list | User manegement | x |  |  |  |  | x |  |  |  |  | View account list Search account | HE163982 | Quản Ngọc Trung | Done | Done | doing | Iter1 | Iter1
9 | Account details | Admin | x |  |  |  |  | x |  |  |  |  | Add new information of user by admin | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter1 | Iter1
10 | Add new account | Admin | x |  |  |  |  | x |  |  |  |  | Add new account by admin | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter1 | Iter1 | Iter4 | - Do not allow new user's password to enter, replace it with gmail and send password to their gmail
11 | Setting List | Admin | x |  |  |  |  | x | x |  |  |  | View setting | HE161340 | Nguyễn Phương Duy | To-Do | Done | Done | Iter1 | Iter1 | Iter4 | Thêm search, Filter
12 | Setting Details | Admin | x |  |  |  |  | x | x |  |  |  | Create new or edit setting | HE161340 | Nguyễn Phương Duy | To-Do | Done | Done | Iter1 | Iter1 | Iter4 | Thêm add
13 | Curriculum List | Manager Curriculum |  | x | [8 empty] | View Curriculum - Search by code - Search by name | HE160555 | Trần Đình Hiệp | Done | Doing | Doing | Iter1 | Iter2 | Iter4 | - Update infor decision
14 | New Curriculum | Manager Curriculum |  | x | [8 empty] | New Curriculum - Create curriculum | HE160555 | Trần Đình Hiệp | Done | Doing | Doing | Iter2 | Iter2 | Iter4 | - Xóa trường dữ liệu Decision - Thêm assigne - Add xong back về list + toast
15 | Curiculum Overview | Manager Curriculum |  | x | [8 empty] | Curriculum Overview - view overview of curriculum | HE160555 | Trần Đình Hiệp | Done | Doing | Doing | Iter2 | Iter2 | Iter4 | - Thêm trường dữ liệu EName
16 | Curiculum Edit | Manager Curriculum |  | x | [8 empty] | Curriculum Edit - Edit infomation of curriculum | HE160555 | Trần Đình Hiệp | Done | Doing | Doing | Iter2 | Iter2 | Iter4 | - Các trường bắt buộc để * - Update thành Công => Hiện toast
17 | PLO_List | Common |  | x | [8 empty] | View plo | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter2 | Iter2 | Iter4 | - Add search, pagging
18 | PLO_Details | Manager Curriculum |  | x | [8 empty] | Edit information of plo | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter2 | Iter2 | Iter4 | - Add toast , allow state changes to be just outside the list , the id of the plo automatically increases, check regex length
19 | PLO_Import | Manager Curriculum |  | x | [8 empty] | Add list plo | HE163795 | Nguyễn Đức Linh | Doing | Doing | Doing | Iter2 | Iter4
20 | PLO_PO_Mapping | Common |  | x | [8 empty] | View plo_po mapping | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter2 | Iter2 | Iter4 | - Show toast after update
21 | PLO_Subject_Mapping | Common |  | x | [8 empty] | View plo_subject mapping | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter2 | Iter3 | Iter4 | - Show toast after update
22 | Suject import | Subject Management |  |  |  | x | [6 empty] | Suject import | HE163982 | Quản Ngọc Trung | Doing | Doing | Doing | Iter2 | Iter3
23 | Subject Details | Subject Management |  | x |  | x | [6 empty] | Subject Details | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter2 | Iter2
24 | New Crriculum Subject | Curriculum Subject Management |  | x | [8 empty] | New Crriculum Subject | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter2 | Iter2 | Iter4 | - add content group.
25 | Crriculum Subject Details | Curriculum Subject Management |  | x | [8 empty] | Crriculum Subject Details | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter2 | Iter2 | Iter4 | - update feature select syllabus and add,update creator. - update UI.
26 | Subject list | Subject Management |  | x |  | x | [6 empty] | Subject list | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter2 | Iter2
27 | Decision list | Decision Manager |  |  |  |  | x | [5 empty] | Decision List - Search by decision_no - Search by approved date null | HE160555 | Trần Đình Hiệp | Done | Done | Done | Iter3 | Iter3
28 | Decision overview | Decision Manager |  | x |  |  | x | [5 empty] | Decision overview - view decision | HE160555 | Trần Đình Hiệp | Done | Done | Done | Iter3 | Iter3
29 | New Decision | Decision Manager |  |  |  |  | x | [5 empty] | New Decision - AddnewDecision | HE160555 | Trần Đình Hiệp | Done | Done | Done | Iter3 | Iter3 | Iter4 | - Nhập được date theo yêu cầu
30 | Decision detail | Decision Manager |  |  |  |  | x | [5 empty] | Decision detail - Edit decision - Update decision for curriculum | HE160555 | Trần Đình Hiệp | Done | Done | Done | Iter3 | Iter3 | Iter4 | - Không show decision_id
31 | Syllabus List | Syllabus Management |  |  | x | [7 empty] | User can view list of syllabus | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter3 | Iter3
32 | Syllabus Overview | Syllabus Management |  |  | x | [7 empty] | User can view overview of syllabus | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter3 | Iter3
33 | New Syllabus | Syllabus Management |  |  | x | [7 empty] | User can add new syllabus | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter3 | Iter3
34 | Syllabus Import | Syllabus Management |  |  | x | [7 empty] | User can add list of syllabus | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter3 | Iter3
35 | Content List | Manager Curriculum |  | x | [8 empty] | View content list | HE163528 | Nguyễn Tiến Thành | Done | Done | Done | Iter3 | Iter3
36 | Content Detail | Manager Curriculum |  | x | [8 empty] | View content detail | HE163528 | Nguyễn Tiến Thành | Done | Done | Done | Iter3 | Iter3
37 | Subject Predecessors | Subject Predecessors Management | [9 empty] | x | VIew subject predecessors | HE163528 | Nguyễn Tiến Thành | Done | Done | Done | Iter3 | Iter3
38 | Subject Successors | Subject Successors Management | [7 empty] | x |  |  | VIew subject successors | HE163528 | Nguyễn Tiến Thành | Done | Done | Done | Iter3 | Iter3 | Iter4 | Add list of subject successors for each subject
39 | Import CLO | Syllabus Management |  |  | x | [7 empty] | View plo_subject mapping | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter3 | Iter3 | Iter4 | add toast after update successfull
40 | CLOs_PLOs | Common |  |  | x | [8 empty] | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter3 | Iter3 | Iter4 | add toast after update successfull
41 | CLO Details | Common |  |  | x | [7 empty] | Admin can edit clo | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter3 | Iter3 | Iter4 | Change type have confirm
42 | CLO List | Common | [10 empty] | View clo list | HE163795 | Nguyễn Đức Linh | Done | Done | Done | Iter3 | Iter3 | Iter4 | add toast after update successfull
43 | Combo List | Manager Curriculum |  | x | [8 empty] | View combo list | HE163528 | Nguyễn Tiến Thành | Done | Done | Done | Iter3 | Iter3 | Iter4 | add combo list outside curriculum
44 | Combo Detail | Manager Curriculum |  | x | [8 empty] | View combo detail | HE163528 | Nguyễn Tiến Thành | Done | Done | Done | Iter3 | Iter3 | Iter4 | add combo detail outside curriculum
45 | PO_List | Common |  | x |  |  |  | x |  |  |  |  | View po | HE161340 | Nguyễn Phương Duy | Done | Done | Done | Iter2 | Iter2 | Iter4 | Update search by active
46 | PO_Details | Manager Curriculum |  | x |  |  |  | x |  |  |  |  | Edit information of po | HE161340 | Nguyễn Phương Duy | Done | Done | Done | Iter2 | Iter2 | Iter4 | Update add po
47 | Elective_List | Common |  | x |  |  |  | x |  |  |  |  | View Elective | HE161340 | Nguyễn Phương Duy | Done | Done | Done | Iter3 | Iter3 | Iter4 | Update elective subject,search by active
48 | Elective_Details | Manager Curriculum |  | x |  |  |  | x |  |  |  |  | Edit information of Elective and subject in elective | HE161340 | Nguyễn Phương Duy | Done | Done | Done | Iter3 | Iter3 | Iter4 | Update add elective and detail
49 | Submit_List | Common |  |  | x | [5 empty] | x |  | View Submit list | HE161340 | Nguyễn Phương Duy | Done | Done | Done | Iter 4 | Iter 4 | Iter4
50 | Submit_Details, Discustion | Manager Curriculum |  |  | x | [5 empty] | x |  | Edit information of Submit | HE161340 | Nguyễn Phương Duy | Done | Done | Done | Iter 4 | Iter 4 | Iter4
51 | Curiculum Subject List | Curriculum Subject Management |  | x | [8 empty] | View Curiculum Subject | HE163982 | Quản Ngọc Trung | Done | Done | Done | Iter 4 | Iter 4
52 | New Subject | Admin |  | x |  | x | [6 empty] | Add new subject | HE163528 | Nguyễn Tiến Thành | Done | Done | Done | Iter2 | Iter2 | Iter4 | Update ui and delete unnecessary data fileds
53 | List Quesiton | View List Question | [10 empty] | View List Question | HE160555 | Trần Đình Hiệp | Done | Done | Done | iter4 | iter4
54 | Question detail | Edit question | [10 empty] | Edit question | HE160555 | Trần Đình Hiệp | Done | Done | Done | iter4 | iter4

## Iter1
Interation1
NO. | Screen / Function Name | Student No | In-charge | Status | NOTES
1 | Home page | HE160555 | Trần Đình Hiệp | DONE
2 | Register | HE163982 | Quản Ngọc Trung | DONE
3 | User Login/ Logout | HE163528 | Nguyễn Tiến Thành | DONE
4 | User Authorization | HE163528 | Nguyễn Tiến Thành | DONE
5 | Change Password | HE163795 | Nguyễn Đức Linh | DONE
6 | Reset Password | HE163795 | Nguyễn Đức Linh | DONE
7 | View profile user | HE160555 | Trần Đình Hiệp | DONE
8 | Account list | HE163982 | Quản Ngọc Trung | DONE
9 | Account details | HE163795 | Quản Ngọc Trung | DONE
10 | Setting List | HE161340 | Nguyễn Phương Duy | DONE
11 | Setting Details | HE161340 | Nguyễn Phương Duy | DONE
12 | Register list | HE163982 | Quản Ngọc Trung | Close
13 | Curriculum List | HE160555 | Trần Đình Hiệp | DONE

## Iter2
Interation2
NO. | Screen / Function Name | Student No | In-charge | Status | NOTES
1 | User Profile | He160555 | Hieptd | Done
2 | Curriculum List | He160555 | Hieptd | Done
3 | New Curriculum | He160555 | Hieptd | Done
4 | Curiculum Overview | He160555 | Hieptd | Done
5 | Curiculum Edit | He160555 | Hieptd | Done
6 | PLO_List | HE163795 | Linh | Done
7 | PLO_Details | HE163795 | Linh | Done
8 | PLO_Import | HE163795 | Linh | Doing
9 | PLO_PO_Mapping | HE163796 | Linh | Done
10 | PLO_Subject_Mapping | HE163797 | Linh | Doing
11 | PO_List | HE161340 | Duynp | Done
12 | PO_Details | HE161340 | Duynp | Done
13 | PO_Import | HE161340 | Duynp | Doing
14 | Subject list | He163982 | TrungQn | Done
15 | New Subject | He163528 | Thanhnt | Done
16 | Suject import | He163982 | TrungQn | To-Do
17 | Subject Details | He163982 | TrungQn | Done
18 | New Crriculum Subject | He163982 | TrungQn | Done
19 | Crriculum Subject Details | He163982 | TrungQn | Done
20 | Sucject Predecessors | He163528 | Thanhnt | To-Do
21 | Sucject Successors | He163528 | Thanhnt | To-Do
22 | Combo List | He163528 | Thanhnt | Done
23 | Combo Details | He163528 | Thanhnt | Done
24 | Elective list | HE161340 | Duynp | Done
25 | Elective detail | HE161340 | Duynp | DONE

## Iter3
Interation3
NO. | Screen / Function Name | Student No | In-charge | Status | NOTES
1 | Decision list | he160555 | hieptd | Done
2 | Decision overview | he160555 | hieptd | Done
3 | New Decision | he160555 | hieptd | Done
4 | Decision detail | he160555 | hieptd | Done
5 | CLO List | he163795 | linhnd | Done
6 | CLO Details | he163795 | linhnd | Done
7 | CLO-PLO Mapping | he163795 | linhnd | Done
8 | CLO import | he163795 | linhnd | Done
9 | PLO import | he163795 | linhnd | Doing
10 | PLO_Subject_Mapping | he163795 | linhnd | Done
11 | Sucject Predecessors | He163528 | Thanhnt | Done
12 | Sucject Successors | He163528 | Thanhnt | Done
13 | Content Group List | He163528 | Thanhnt | Done
14 | Content Group Detail | He163528 | Thanhnt | Done
15 | Syllabus List | HE163982 | Trungqn | Done
16 | Syllabus Overview | HE163982 | Trungqn | Done
17 | New Syllabus | HE163982 | Trungqn | Done
18 | Subject Import | HE163982 | Trungqn | Doing
19 | Syllabus Import | HE163982 | Trungqn | Done
20 | Elective Detail | HE161340 | DuyNP | Done
21 | Submit List | HE161340 | DuyNP | Doing
22 | Submit Detail | HE161340 | DuyNP | Doing
23 | Submit Discussion | HE161340 | DuyNP | Doing

## Iter4
Interation4
NO. | Screen / Function Name | Student No | In-charge | Status | NOTES
1 | Assessment list | HE163982 | TrungQN | TO-DO
2 | assessment Details | HE163982 | TrungQN | TO-DO
3 | Subject Import | HE163982 | TrungQN | TO-DO
4 | Syllabus Edit | HE163982 | TrungQN | TO-DO
5 | Curiculum Subject List | HE163982 | TrungQN | Done
6 | Question List | HE160555 | HiepTD | Done
7 | Question Detail | HE160555 | HiepTD | Done
8 | Question Import | HE160555 | HiepTD | Pending
9 | PLO import | HE163795 | LinhND | Done
10 | Material List | HE163796 | LinhND | Pending
11 | Material Details | HE163797 | LinhND | Pending
12 | Submit List | HE161340 | DuyNP | Pending
13 | Submit Detail | HE161340 | DuyNP | Pending
14 | Submit Discussion | HE161340 | DuyNP | Pending
15 | Elective Update | HE161340 | DuyNP | Done
15