## Issues Report
Title | Description | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
User Login Screen | A form with fields for the user to enter their email or username or phone and password. Include a "forgot password" link or button for users who may have forgotten their login information. Besides, you can quickly login with Google. After users enter their credentials, the data processing part of the credentials involves verifying the entered information against the data stored in the system. This can be done by checking a database or other storage location for the right email, username, or phone and password combination. | Closed | ThanhNTHE163528 | 2023-05-23 | 2023-05-28 | iter1 | WP, 3_Done | User Login
Write SRS for User Login screen | Write detailed functional specification for the User Login screen | Closed | ThanhNTHE163528 | 2023-05-23 | 2023-05-28 | iter1 | Task, 3_Done | User Login
Write SDS for User Login screen | Write detailed code design (class diagram, class specifications, sequence diagram, SQL) for the User Login screen | Closed | ThanhNTHE163528 | 2023-05-23 | 2023-05-28 | iter1 | Task, 3_Done | User Login
Write Code for User Login screen | Code & Unit test for the User Login screen | Closed | ThanhNTHE163528 | 2023-05-23 | 2023-05-28 | iter1 | Task, 3_Done | User Login
Integrate User Login screen with others | Integrate the User Login screen with other screens | Closed | ThanhNTHE163528 | 2023-05-23 | 2023-05-28 | iter1 | Task, 3_Done | User Login
Hompage screen | A page that opens when the user is logged in or not logged in to perform functions | Closed | hieptdhe160555 | 2023-05-23 | 2023-05-28 | iter1 | WP, 3_Done | Hompage
Write SRS for Homepage | Write detailed functional specification for the hompage | Closed | hieptdhe160555 | 2023-05-23 | 2023-05-28 | iter1 | Task, 3_Done | Hompage
Write SDS for Homepage | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for the hompage | Closed | hieptdhe160555 | 2023-05-23 | 2023-05-28 | iter1 | Task, 3_Done | Hompage
Write Code for Homepage | Code & Unit test for the User Login screen | Closed | hieptdhe160555 | 2023-05-23 | 2023-05-28 | iter1 | Task, 3_Done | Hompage
Connect from Homepage | Connect to login, register, profile setting, logout | Closed | hieptdhe160555 | 2023-05-23 | 2023-05-28 | iter1 | Task, 3_Done | Hompage
Write SRS for Reset Password screen | Write detailed functional specification for the Reset Password screen | Closed | LinhND | 2023-05-25 | 2023-05-28 | iter1 | Task, 3_Done | Reset Password
Write SDS for Reset Password screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Reset Password screen | Closed | LinhND | 2023-05-25 | 2023-05-28 | iter1 | Task, 3_Done | Reset Password
Write Code for Reset Password screen | Code & Unit test for the Reset Password screen | Closed | LinhND | 2023-05-25 | 2023-05-28 | iter1 | Task, 3_Done | Reset Password
Write SRS for change password screen | This is a pop-up screen which allows the user change your password | Closed | LinhND | 2023-05-25 | 2023-05-28 | iter1 | Task, 3_Done | Change Password
Write SDS for change password screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for change Password pop-up | Closed | LinhND | 2023-05-25 | 2023-05-28 | iter1 | Task, 3_Done | Change Password
Write Code for change password screen | Code & Unit test for the change Password pop-up | Closed | LinhND | 2023-05-25 | 2023-05-28 | iter1 | Task, 3_Done | Change Password
Write SRS for account details screen | This is a screen which allows the admin add new user | Closed | LinhND | 2023-05-25 | 2023-05-28 | iter1 | Task, 3_Done | Add new user
Write SDS for account details screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for account details screen | Closed | LinhND | 2023-05-25 | 2023-05-28 | iter1 | Task, 3_Done | Add new user
Write Code for account details screen | Code & Unit test for account details screen | Closed | LinhND | 2023-05-25 | 2023-05-28 | iter1 | Task, 3_Done | Add new user
Write Code for User Register | Write Code for User Register | Closed | TrungQN | 2023-05-21 | 2022-05-28 | iter1 | Req, 3_Done | User Register
Write Code for Account list | Write Code for Account list | Closed | TrungQN | 2023-05-21 | 2022-05-28 | iter1 | Req, 3_Done | Account List
Write SDS for User Register | Write SDS for User Register | Closed | TrungQN | 2023-05-21 | 2022-05-28 | iter1 | Task, 3_Done | User Register
Write SRS for User Register | Write SRS for User Register | Closed | TrungQN | 2023-05-21 | 2022-05-28 | iter1 | Task, 3_Done | User Register
Connect Account List Screen With Other Screen | Connect Account List Screen With Other Screen | Closed | TrungQN | 2023-05-21 | 2022-05-28 | iter1 | Req, 3_Done | Account List
Connect Register Screen With Other Screen | Connect Register Screen With Other Screen | Closed | TrungQN | 2023-05-21 | 2022-05-28 | iter1 | Req, 3_Done | User Register
Write SDS for Account list | Write SDS for Account list | Closed | TrungQN | 2023-05-21 | 2022-05-28 | iter1 | Task, 3_Done | Account List
Write SRS for Account list | Write SRS for Account list | Closed | TrungQN | 2023-05-21 | 2022-05-28 | iter1 | Task, 3_Done | Account List
Write SDS for Setting list | Write SDS for Setting list | Closed | DuyNP | 2023-05-21 | 2022-05-28 | iter1 | Task, 3_Done | Setting List
Write SRS for Setting list | Write SRS for Setting list | Closed | DuyNP | 2023-05-21 | 2022-05-28 | iter1 | Task, 3_Done | Setting List
Write SDS for Setting detail | Write SDS for Setting detail | Closed | DuyNP | 2023-05-21 | 2022-05-28 | iter1 | Task, 3_Done | Setting detail
Write SRS for Setting detail | Write SRS for Setting detail | Closed | DuyNP | 2023-05-21 | 2022-05-28 | iter1 | Task, 3_Done | Setting detail
Connect Setting List Screen With Other Screen | Connect Setting List Screen With Other Screen | Closed | DuyNP | 2023-05-21 | 2022-05-28 | iter1 | Req, 3_Done | Setting List
Connect Setting Detail Screen With Other Screen | Connect Setting Detail Screen With Other Screen | Closed | DuyNP | 2023-05-21 | 2022-05-28 | iter1 | Req, 3_Done | Setting Detail
Write Code for Setting list | Write Code for Setting list | Closed | DuyNP | 2023-05-21 | 2022-05-28 | iter1 | Req, 3_Done | Setting List
Write Code for Setting Detail | Write Code for Setting Detail | Closed | DuyNP | 2023-05-21 | 2022-05-28 | iter1 | Req, 3_Done | Setting Detail
Write SRS for List PLOs screen | Write detailed functional specification for the List PLOs screen | Closed | LinhND | 2023-06-07 | 2023-06-11 | iter1 | Task, 3_Done | List PLO
Write SDS for List PLOs screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for List PLO screen | Closed | LinhND | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | List PLO
Write Code for List PLOs screen | Code & Unit test for the List PLOs screen | Closed | LinhND | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | List PLO
Write SRS for List PLOs screen | This is a screen which allows the user to see the list PLOs | Closed | LinhND | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | PLOs Details
Write SDS for PLOs Details (CRUD) screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for PLOs Details screen | Closed | LinhND | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | PLOs Details
Write Code for PLOs Details screen | Code & Unit test for the change Password pop-up | Closed | LinhND | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | PLOs Details
Write SRS for Po_Plo Mapping screen | This is a screen which allows the admin change change the association between plo_po and for user the screen will show association between plo_po | Closed | LinhND | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | Po_Plo Mapping
Write SDS Po_Plo Mapping screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Po_Plo Mapping screen | Closed | LinhND | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | Po_Plo Mapping
Write Code for Po_Plo Mapping screen | Code & Unit test for Po_Plo Mapping screen | Closed | LinhND | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | Po_Plo Mapping
Write SDS for Add New Subject screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for New Subject screen | Closed | ThanhNTHE163528 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | New Subject
Write Code for Add New Subject screen | Code & Unit test for the New Subject screen | Closed | ThanhNTHE163528 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | New Subject
Write SRS for Add New Subject screen | This is a screen which allows the admin add new subject | Closed | ThanhNTHE163528 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | New Subject
Write SDS for Combo List screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Combo List screen | Closed | ThanhNTHE163528 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | Combo List
Write Code for Combo List screen | Code & Unit test for the Combo List Screen | Closed | ThanhNTHE163528 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | Combo List
Write SRS for Combo List screen | This is a screen which allows the user view list combo | Closed | ThanhNTHE163528 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | Combo List
Write SDS for Combo Detail screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Combo Detail screen | Closed | ThanhNTHE163528 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | Combo Detail
Write Code for Combo Detail screen | Code & Unit test for the Combo Detail Screen | Closed | ThanhNTHE163528 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | Combo Detail
Write SRS for Combo Detail screen | This is a screen which allows the user view detail combo, list subject combo | Closed | ThanhNTHE163528 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | Combo Detail
Write SRS for List POs screen | Write detailed functional specification for the List POs screen | Closed | DuyNP | 2023-06-07 | 2023-06-11 | iter1 | Task, 3_Done | List PO
Write SDS for List POs screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for List PO screen | Closed | DuyNP | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | List PO
Write Code for List POs screen | Code & Unit test for the List POs screen | Closed | DuyNP | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | List PO
Write SRS for List POs screen | This is a screen which allows the user to see the list POs | Closed | DuyNP | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | POs Details
Write SDS for POs Details (CRUD) screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for POs Details screen | Closed | DuyNP | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | POs Details
Write Code for POs Details screen | Code & Unit test for the change Password pop-up | Closed | DuyNP | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | POs Details
List Curriculum | List Curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | List Curriculum
Srs for curriculum | Srs for curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | List Curriculum
Sds for curriculum | Sds for curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | List Curriculum
code of list curriculum | Code of list curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | List Curriculum
connect other screen with list curriculum | Connect other screen with list curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | List Curriculum
New curriculum | New curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Task, 3_Done | New curriculum
Srs for new curriculum | Srs for new curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | New curriculum
Sds for new curriculum | Sds for new curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | New curriculum
code of new curriculum | Code of new curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | New curriculum
connect other screen with new curriculum | Connect other screen with new curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | New curriculum
Edit curriculum | Edit curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Task,3_Done | Edit curriculum
Srs for edit curriculum | Srs for edit curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | Edit curriculum
Sds for edit curriculum | Sds for edit curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | Edit curriculum
code of edit curriculum | Code of edit curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | Edit curriculum
connect other screen with edit curriculum | Connect other screen with edit curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | Edit curriculum
Overview Curriculum | Overview Curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Task,3_Done | Overview Curriculum
Srs for overview curriculum | Srs for overview curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | Overview Curriculum
Sds for overview curriculum | Sds for overview curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | Overview Curriculum
code of overview curriculum | Code of overview curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | Overview Curriculum
connect other screen with overview curriculum | Connect other screen with overview curriculum | DONE | hieptdhe160555 | 2023-06-07 | 2023-06-11 | iter2 | Req, 3_Done | Overview Curriculum
Decision overview | Decision overview | DONE | hieptdhe160555 | 2023-06-17 | 2023-06-22 | iter3 | Task, 3_Done | Decision overview
Srs decision overview | Srs decision overview | DONE | hieptdhe160555 | 2023-06-17 | 2023-06-22 | iter3 | Req, 3_Done | Decision overview
Sds decision overview | Sds decision overview | DONE | hieptdhe160555 | 2023-06-17 | 2023-06-22 | iter3 | Req, 3_Done | Decision overview
code of decision overview | Code of decision overview | DONE | hieptdhe160555 | 2023-06-17 | 2023-06-22 | iter3 | Req, 3_Done | Decision overview
connect decision overview with other screen | Connect decision overview with other screen | DONE | hieptdhe160555 | 2023-06-17 | 2023-06-22 | iter3 | Req, 3_Done | Decision overview
Decision list | Decision list | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Task,3_Done | Decision list
Srs decision List | Srs decision List | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | Decision list
Sds decision List | Sds decision List | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | Decision list
code of decision list | Code of decision list | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | Decision list
connect decision list with other screen | Connect decision list with other screen | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | Decision list
Decision detail | Decision detail | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Task, 3_Done | Decision detail
Srs decision detail | Srs decision detail | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | Decision detail
Sds decision detail | Sds decision detail | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | Decision detail
code of decision detail | Code of decision detail | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | Decision detail
connect decision detail with other screen | Connect decision detail with other screen | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | Decision detail
new decision | New decision | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Task,3_Done | New decision
Srs new decision | Srs new decision | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | New decision
Sds new decision | Sds new decision | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | New decision
code of new decision | Code of new decision | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | New decision
connect new decision with other screen | Connect new decision with other screen | DONE | hieptdhe160555 | 2023-06-20 | 2023-06-22 | iter3 | Req, 3_Done | New decision
SRS For Import CLO | This is a screen which allows the admin import the list CLOs | DONE | LinhNDhe163795 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | Import CLO
SDS For Import CLO | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Import CLO screen | DONE | LinhNDhe163796 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | Import CLO
SRS List CLO | This is a screen which allows the user to see the list CLOs | DONE | LinhNDhe163797 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | List CLO
SDS List CLO | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for List CLO screen | DONE | LinhNDhe163798 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | List CLO
SRS CLO Details | This is a screen which allows the admin change,update,delete clo | DONE | LinhNDhe163799 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | CLO Details
SDS CLO Details | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for CLO Details screen | DONE | LinhNDhe163800 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | CLO Details
SRS Mapping CLO_PLO | This is a screen which allows the admin change change the association between clo_plo and for user the screen will show association between clo_plo | DONE | LinhNDhe163801 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | Mapping CLO_PLO
SDS Mapping CLO_PLO | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Mapping PLO_CLO screen | DONE | LinhNDhe163802 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | Mapping CLO_PLO
SRS Mapping Subject_PLO | This is a screen which allows the admin change change the association between Subject_Plo and for user the screen will show association between Subject_Plo | DONE | LinhNDhe163803 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | Mapping Subject_PLO
SDS Mapping Subject_PLO | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Mapping Subject_PLO screen | DONE | LinhNDhe163804 | 2023-06-12 | 2023-06-24 | iter3 | Task, 3_Done | Mapping Subject_PLO
SRS Content List | This is a screen which allows the user view list content (search, filter), admin can add new,update,delete content group | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Content List
SRS Content Detail | This is a screen which allows the user view list subject content (search, filter), admin can add new,update subject to content group and delete subject content | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Content Detail
SRS Subject Predecessors | This is a screen which allows the user view subject predecessors | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Subject Predecessors
SRS Subject Successors | This is a screen which allows the user view subject successors | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Subject Successors
SDS Content List | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Content List | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Content List
SDS Content Detail | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Content Detail | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Content Detail
SDS Subject Predecessors | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Subject Predecessors | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Subject Predecessors
SDS Subject Successors | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Subject Successors | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Subject Successors
Code For Content List | Code of screen content list | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Content List
Code For Content Detail | Code of screen content detail | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Content Detail
Code For Subject Predecessors | Code of screen subject predecessors | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Subject Predecessors
Code For Subject Successors | Code of screen subject successors | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Subject Successors
Connect Content List with another screen | Connect screen content list with Screen content detail | DONE | ThanhNTHE163528 | 2023-06-12 | 2023-06-26 | iter3 | Task, 3_Done | Content List
SRS Syllabus List | SRS Syllabus List | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Task,Done | Syllabus List
SRS Syllabus Overview | SRS Syllabus Overview | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Task,Done | Syllabus Overview
SRS Add New Syllabus | SRS Add New Syllabus | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Task,Done | Add New Syllabus
SRS Import Syllabus | SRS Import Syllabus | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Task,Done | Import Syllabus
SDS Syllabus List | SDS Syllabus List | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Task,Done | Syllabus List
SDS Syllabus Overview | SDS Syllabus Overview | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Task,Done | Syllabus Overview
SDS Add New Syllabus | SDS Add New Syllabus | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Task,Done | Add New Syllabus
SDS Import Syllabus | SDS Import Syllabus | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Task,Done | Import Syllabus
Code For Syllabus List | Code For Syllabus List | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Req,Done | Syllabus List
Code For Syllabus Overview | Code For Syllabus Overview | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Req,Done | Syllabus Overview
Code For Add New Syllabus | Code For Add New Syllabus | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Req,Done | Add New Syllabus
Code For Import Syllabus | Code For Import Syllabus | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Req,Done | Import Syllabus
connect other screen for Syllabus List | connect other screen for Syllabus List | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Req,Done | Syllabus List
connect other screen for Syllabus Overview | connect other screen for Syllabus Overview | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Req,Done | Syllabus Overview
connect other screen for Add New Syllabus | connect other screen for Add New Syllabus | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Req,Done | Add New Syllabus
connect other screen for Import Syllabus | connect other screen for Import Syllabus | DONE | trungqnhe163982 | 2023-06-12 | 2023-06-26 | iter3 | Req,Done | Import Syllabus
Write SDS for Elective List screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Elective List screen | DONE | DuyNp | 2023-06-25 | 2023-06-26 | iter3 | Task, 3_Done | Elective List
Write Code for Elective List screen | Code & Unit test for the Elective List Screen | DONE | DuyNp | 2023-06-25 | 2023-06-26 | iter3 | Task, 3_Done | Elective List
Write SRS for Elective List screen | This is a screen which allows the user view list Elective | DONE | DuyNp | 2023-06-25 | 2023-06-26 | iter3 | Task, 3_Done | Elective List
Write SDS for Elective Detail screen | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Elective Detail screen | DONE | DuyNp | 2023-06-25 | 2023-06-26 | iter3 | Task, 3_Done | Elective Detail
Write Code for Elective Detail screen | Code & Unit test for the Elective Detail Screen | DONE | DuyNp | 2023-06-25 | 2023-06-26 | iter3 | Task, 3_Done | Elective Detail
Write SRS for Elective Detail screen | This is a screen which allows the user view detail Elective , list subject Elective | DONE | DuyNp | 2023-06-25 | 2023-06-26 | iter3 | Task, 3_Done | Elective Detail
connect other screen for Elective List | connect other screen for Elective List | DONE | DuyNp | 2023-06-25 | 2023-06-26 | iter3 | Task, 3_Done | Elective List
connect other screen for Elective Detail | connect other screen for Elective Detail | DONE | DuyNp | 2023-06-25 | 2023-06-26 | iter3 | Task, 3_Done | Elective Detail
Question List | Question List | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Task, 3_Done | Question List
Srs for question list | Srs for question list | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Req, 3_Done | Question List
Sds for question list | Sds for question list | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Req, 3_Done | Question List
code of question list | Code of question list | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Req, 3_Done | Question List
connect question list to other screen | Connect question list to other screen | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Req, 3_Done | Question List
Question Detail | Question Detail | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Task, 3_Done | Question Detail
Srs for question detail | Srs for question detail | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Req, 3_Done | Question Detail
Sds for question detail | Sds for question detail | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Req, 3_Done | Question Detail
code of question detail | Code of question detail | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Req, 3_Done | Question Detail
connect question detail to other screen | Connect question detail to other screen | DONE | hieptdhe160555 | 2023-07-19 | 2023-07-21 | iter4 | Req, 3_Done | Question Detail
Srs for curriculum Subject List | Srs for curriculum Subject List | DONE | trungqnhe163982 | 2023-07-19 | 2023-07-21 | iter4 | Task,Done | Curriculum Subject Manegement
Sds for curriculum Subject List | Sds for curriculum Subject List | DONE | trungqnhe163982 | 2023-07-19 | 2023-07-21 | iter4 | Task,Done | Curriculum Subject Manegement
code of curriculum Subject List | code of curriculum Subject List | DONE | trungqnhe163982 | 2023-07-19 | 2023-07-21 | iter4 | Req,Done | Curriculum Subject Manegement
connect curriculum Subject List | connect curriculum Subject List | DONE | trungqnhe163982 | 2023-07-19 | 2023-07-21 | iter4 | Task,Done | Curriculum Subject Manegement
SRS For Import PLO | This is a screen which allows the admin import the list PLOs | DONE | LinhNDhe163795 | 2023-06-12 | 2023-06-24 | iter4 | Task, 3_Done | Import CLO
SDS For Import PLO | Write detailed codde design (class diagram, class specifications, sequence diagram, SQL) for Import PLO screen | DONE | LinhNDhe163796 | 2023-06-12 | 2023-06-24 | iter4 | Task, 3_Done | Import CLO